## 📊 Summary
📊 Weekly Status Summary — Developer View
Fill each week's sheet → use this summary for stand-ups & sprint reviews
W1 – 19 May
Developer | Team | Completed | In Progress | Blocked | Pending | Not Started | Total Tasks
Khizar | Frontend
Adittiya | Frontend
Tabrez | Frontend
Dev 1 | Backend
Dev 2 | Backend
QA 1 | QA
QA 2 | QA
DevOps 1 | DevOps
W2 – 26 May
Developer | Team | Completed | In Progress | Blocked | Pending | Not Started | Total Tasks
Khizar | Frontend
Adittiya | Frontend
Tabrez | Frontend
Dev 1 | Backend
Dev 2 | Backend
QA 1 | QA
QA 2 | QA
DevOps 1 | DevOps
W3 – 02 Jun
Developer | Team | Completed | In Progress | Blocked | Pending | Not Started | Total Tasks
Khizar | Frontend
Adittiya | Frontend
Tabrez | Frontend
Dev 1 | Backend
Dev 2 | Backend
QA 1 | QA
QA 2 | QA
DevOps 1 | DevOps
W4 – 09 Jun
Developer | Team | Completed | In Progress | Blocked | Pending | Not Started | Total Tasks
Khizar | Frontend
Adittiya | Frontend
Tabrez | Frontend
Dev 1 | Backend
Dev 2 | Backend
QA 1 | QA
QA 2 | QA
DevOps 1 | DevOps
W5 – 16 Jun
Developer | Team | Completed | In Progress | Blocked | Pending | Not Started | Total Tasks
Khizar | Frontend
Adittiya | Frontend
Tabrez | Frontend
Dev 1 | Backend
Dev 2 | Backend
QA 1 | QA
QA 2 | QA
DevOps 1 | DevOps

## W1 – 19 May
AML Design and Framework
Day | Date | Team | Developer | Module | Sub Module/ Task Title | Dev Phases | Description / Update | Status | Blockers / Notes | ETA / Due
Monday | 2026-05-18 | 2026-05-18 | Khizar | KYC | Customer 360 View | Design - Prepare BFF/API requirement documentation, including endpoint definitions | 1- Completed top-down implementation of Customer 360 main view structure and integrated the overall UI layout. 2- Configured and validated all Customer 360 tabs to ensure proper routing and rendering flow. 3- Analyzed the existing API structure and started breaking APIs at the tab level in KYC BFF for better scalability and lazy loading. 4- Identified heavy modules like Transactions, Alerts, and Audit Logs for pagination-based API planning and performance optimization. | Completed | Non | 2026-05-19
|  |  | Aditya | KYC | Customer 360 View | Customer 360 View UI Development | Accounts & Transactions — Account table plus limits/holdings; filterable txn list with CSV export and links to alerts. Alerts — Open/critical summary, expandable alert cards, history, funding-source bars. Reg Reports · KYC Gap · Audit — STR/CTR/FEMA/LEA tables; gap score and missing fields with export; full audit log. Lookup screen and Individual/Corporate demo data included; some fields can load from API when available. | Completed | None | 2026-05-18
|  |  | Tabrez | KYC | Customer 360 View | Customer 360 View UI Development | • Header & Shell: Top navigation with 11 tabs, customer banner (name, IDs, risk score), clickable alert flags for quick navigation, and reveal/mask support for ID documents. • Overview: KPI tiles, customer/employment/KYC/address details, masked contact information, risk visualization, relationships & screening summary, transaction metrics, regulatory details, and recent activity. • Relationships / Screening / Risk / KYC-CDD: Family/joint/corporate relationship tables, sanctions/PEP/adverse media/watchlist checks, risk score & history tracking, document verification, trigger alerts, and CDD workflow. | Completed | None | 2026-05-18
|  | Backend | Arun | KYC | Customer 360 View | Customer 360 View Backhand Devlopment | Completed analysis of Customer 360 FRD document. Reviewed UI screens. Identified Individual and Non-Individual customer-specific requirements. | Completed | None | 2026-05-19
|  |  | Santosh | Data Ingestion | AML Data Ingestion Framework | ETL process for Data Ingestion Backhand Devlopment | Working on POC and implementation for AML data ingestion pipeline. Evaluating and developing approaches to ingest and transform data from multiple sources such as file-based systems, databases, and APIs into the master data model for AML processing | In Progress | None | 2026-05-19
|  | QA | Arti Kunde | KYC | KYC/Customer 360 Test Cases | KYC/Customer 360 Test Case writing | Covered test cases for the KYC module, specifically focusing on the Header Strip and Customer Type Switching submodules based on defined workflows, validations, and business requirements. Updated and modified 20 test cases for the Customer 360 View module according to the shared user stories and acceptance criteria, mainly covering Screening Tabs, navigation flow, and functional scenarios.Maintained all test cases in a structured Excel format for easy tracking, execution, and review. | Completed | None | 2026-05-19
|  |  | Sanket Kirar | KYC | KYC/Customer 360 Test Cases | KYC/Customer 360 Test Case writing | Covered 15 test cases for the KYC module, specifically focusing on the "Customer Details" submodule based on defined workflows and requirements. Covered 20 test cases for the Customer 360 View module, mainly validating the Relationship Tabs for functional behavior, navigation, and related scenarios. | Completed | None | 2026-05-19
|  | DevOps | DevOps 1 | HLD | HLD
Tuesday | 2026-05-19 | Frontend | Khizar | KYC | Missing Mandatory Reports | Design - Prepare BFF/API requirement documentation, including endpoint definitions | 1- Started implementation of KYC/Missing Mandatory Reports module UI integration. 2- Working on Missing Mandatory Reports BFF layer setup and API integration flow. 3- Designing tab-level API handling for Missing Mandatory Reports similar to Customer 360 architecture. 4- Analyzing response structure and performance considerations for scalable report rendering. | In Progress | None | 2026-05-20
|  |  | Aditya | KYC | Missing Mandatory Reports | Missing Mandatory Reports UI Development | Individual CIP — 5 groups, 19 fields, locked/editable rules Corporate CIP — 3 groups, 9 fields, Corporate-only CDD — 6 fields, orange section, tags EDD — 5 fields, red section Technical IDs — 9 read-only system fields KYC Gap Score — 4 bands, validation, save Add Custom Field modal Create Template full-page form | Completed | None | 2026-05-20
|  |  | Tabrez | KYC | Missing Mandatory Reports | Missing Mandatory Reports UI Development | • Shell (MM-001–003): Top bar, sidebar navigation (Template + KYC Gap Report), and two-panel layout. • Template List (MM-TL01–02): Grouped Individual/Corporate template list with 8 templates, KYC badges, and template selection. • Detail Header & Tabs (MM-TD01–02): Template name, badge, metadata, Add Field & Save Changes actions, plus Individual/Corporate CIP, CDD, EDD, Technical IDs, and KYC Gap Score tabs with field counts and conditional visibility by template type. | Completed | None | 2026-05-20
|  | Backend | Arun | KYC | Customer 360 View | Customer 360 Data Model & API Development | Analyzed all 11 tabs and their backend data dependencies. Reviewed dynamic customer type switching requirements. Identified API contracts required for Customer 360 dashboard. | Completed | None | 2026-05-20
|  |  | Santosh | Data Ingestion | AML Data Ingestion Framework | ETL process for Data Ingestion Backhand Devlopment | Working on POC and implementation for AML data ingestion pipeline. Evaluating and developing approaches to ingest and transform data from multiple sources such as file-based systems, databases, and APIs into the master data model for AML processing | In Progress | None | 2026-05-20
|  | QA | Arti Kunde | KYC | KYC/Missing Mandatory | KYC/Missing Mandatory test case writing | Covered 28 test cases for the Missing Mandatory module, focusing on remaining Two-Panel Layout and Sidebar Navigation scenarios including panel behavior, navigation flow, search functionality, state persistence, authorization visibility, and UI stability validations. | Completed | None | 2026-05-20
|  |  | Sanket Kirar | KYC | KYC/Missing Mandatory | KYC/Missing Mandatory test case writing | Covered 26 test cases for the Missing Mandatory module, focusing on App Shell – Top Bar and Two-Panel Layout scenarios including UI behavior, navigation controls, layout validation, scrolling functionality, accessibility, and view transitions. | Completed | None | 2026-05-20
|  | DevOps | DevOps 1 |  | Finalising the HDL and Services
Wednesday | 2026-05-20 | Frontend | Khizar | KYC | Missing Mandatory Reports | Design - Prepare BFF/API requirement documentation, including endpoint definitions | Finalized Missing Mandatory Reports BFF API listing and shared the complete details with Arun for BFF layer implementation by EOD.
|  |  | Aditya | KYC | Missing Mandatory Reports | Missing Mandatory Reports UI Development | Individual CIP — 5 groups, 19 fields, locked/editable rules Corporate CIP — 3 groups, 9 fields, Corporate-only CDD — 6 fields, orange section, tags EDD — 5 fields, red section Technical IDs — 9 read-only system fields KYC Gap Score — 4 bands, validation, save Add Custom Field modal Create Template full-page form | Completed | None | 2026-05-20
|  |  | Tabrez | KYC | Missing Mandatory Reports | Missing Mandatory Reports UI Development | • Shell (MM-001–003): Top bar, sidebar navigation (Template + KYC Gap Report), and two-panel layout. • Template List (MM-TL01–02): Grouped Individual/Corporate template list with 8 templates, KYC badges, and template selection. • Detail Header & Tabs (MM-TD01–02): Template name, badge, metadata, Add Field & Save Changes actions, plus Individual/Corporate CIP, CDD, EDD, Technical IDs, and KYC Gap Score tabs with field counts and conditional visibility by template type. | Completed | None | 2026-05-20
|  | Backend | Arun | Data Ingestion | AML Design and Framework | Backend Development for ETL-Based Data Ingestion | Working on POC and implementation for AML data ingestion pipeline. Evaluating and developing approaches to ingest and transform data from multiple sources such as file-based systems, databases, and APIs into the master data model for AML processing Additional details updated in the data ingestion document | Completed |  | 2026-05-21
|  |  | Santosh | KYC | Missing mandatory and KYC gap report | Missing mandatory and KYC gap report for Backhand Devlopment | Analyzed FRD requirements for the module. Started working on HLD and LLD documentation. | In Progress |  | 2026-05-25
|  | QA | Arti Kunde | KYC | KYC/Missing Mandatory | Missing Mandatory test case writing | Working on test case design for Missing Mandatory Data Template, covering template list behavior, grouping logic, template cards, count validations, detail header, tab behavior, selection states, and UI/accessibility-related validations. | In Progress |  | 2026-05-21
|  |  | Sanket Kirar | KYC | KYC/Missing Mandatory | Missing Mandatory test case writing | Working on test case design for Create New Template, covering form behavior, required/optional validations, dropdown logic, clone functionality, version handling, gap score configuration, CTA behavior, and success/cancel flow validations. | In Progress |  | 2026-05-21
|  | DevOps | DevOps 1 |  | Getting the pre-requisite env ready to check for the compatibility with the current server
Thursday | 2026-05-21 | Frontend | Khizar | KYC | KYC Gap Reports | Design - Prepare BFF/API requirement documentation, including endpoint definitions | 1- Started implementation of KYC Gap Reports BFF layer structure and initial API integration flow. 2- Working on tab-level API segregation for KYC Gap Reports to support scalable and modular data loading. 3- Designing frontend-to-BFF integration flow aligned with Customer 360 architecture patterns. 4- Analyzing KYC Gap Reports response structure, pagination strategy, and performance optimization for large report datasets. | In Progress | None | 2026-05-22
|  |  | Adittiya | KYC | KYC Gap Reports | KYC Gap Reports UI Development | Page header with title “KYC Gap Report” and subtitle “Missing or expired KYC fields — CBS & DMS import vs. template requirements” (GapReportHeader). Export outline button with icon in the header (UI in place; wired export of filtered dataset is still a follow-up for MM-GR08). Exactly three KPI cards: Total Customers (CBS), Customers with Gaps (red value + delta sub-label), Critical Priority (red count + “Immediate action required”); no removed v1.1 cards (CDD/EDD triggered gaps, compliance rate). | In Progress | None | 2026-05-22
|  |  | Tabrez | KYC | KYC Gap Reports | KYC Gap Reports UI Development | Dedicated KYC Gap Report route at /kyc/kyc-gap-report via KycGapReportPage, using a full-width layout (not the template two-panel layout) — aligns with MM-002 / MM-GR page structure. Sidebar navigation entry “KYC Gap Report” is registered in the KYC MFE (mf.config.json) and host-generated nav (/kyc/kyc-gap-report) — MM-003. Top bar on gap report view shows label “KYC Gap Report”, global search placeholder, sidebar toggle, and hides “+ Create Template” (showCreateButton={false}) — MM-001 (gap-report slice of shell). | In Progress | None | 2026-05-22
|  | Backend | Arun | KYC | Customer 360 | Customer 360 Data Model | Reviewed and analyzed the AML data model shared by the team. Performed Customer 360 data model analysis based on FRD and UI requirements. Created Flyway migration scripts for database schema and table creation. Set up the backend project structure and database migration framework. Designing database entities and mappings aligned with Customer 360 UI and business requirements. | Completed | None
|  |  | Santosh | KYC | Missing mandatory | Missing mandatory for Backhand Devlopment | Analyzed UI requirements, database tables, and business logic for the Missing Mandatory module. Identified required data sources, validation rules, and report generation logic. | Completed
|  |  | Sushma | Data Ingestion | ETL |  | working on the Data Ingestion module and reviewing its complete end-to-end flow. Currently, I am focusing on understanding the API call flow for the Data Ingestion process. | Completed | None | 2026-05-21
|  | QA | Arti Kunde | KYC | KYC/Missing Mandatory / Gap Reports | Missing Mandatory and Gap Reports test case writing | Yesterday: Worked on test case design for Missing Mandatory Data Template, covering template list behavior, grouping logic, template cards, count validations, detail header, tab behavior, selection states, and UI/accessibility-related validations. Today: Will continue covering Missing Mandatory module test cases focusing on field configuration, Individual and Corporate template behavior, CDD/EDD sections, Technical IDs, field mapping, and validation-related scenarios. | Completed | None | 2026-05-22
|  |  | Sanket Kirar | KYC | KYC/Missing Mandatory / Gap Reports | Missing Mandatory and Gap Reports test case writing | Yesterday: Worked on test case design for Create New Template, covering form behavior, required/optional validations, dropdown logic, clone functionality, version handling, gap score configuration, CTA behavior, and success/cancel flow validations. Today: Will continue covering Missing Mandatory module test cases focusing on versioning, save flow validations, score calculation logic, score mapping, boundary validations, template synchronization, and initial KYC Gap Report-related scenarios. | Completed | None | 2026-05-22
|  | DevOps | DevOps 1 |  | Shared the system requirements based on the architecture
Friday | 2026-05-22 | Frontend | Khizar | KYC | KYC Gap Reports | Design - Prepare BFF/API requirement documentation, including endpoint definitions | Finalized KYC Gap Reports BFF API listing and shared the complete details with Arun for BFF layer implementation by EOD. | In Progress | None | 2026-05-25
|  |  | Aditya | KYC | KYC Gap Reports | KYC Gap Reports UI Development | Gap score display as integer + coloured risk label in the table (gapScoreColor / gapScoreLabel); detail modal shows Weight: 3 (Mandatory) / Weight: 1 (Optional) per missing field. Gap Detail Modal (~580px): title {Customer} — KYC Gap Detail, customer/branch/template info grid, Missing Fields list with Gap Type badge (CIP/CDD/EDD colours), blue Total KYC Gap Score footer, read-only Close + X + overlay close — MM-GR06. Client-side pagination (10 / 20 / 50), from–to of N items, Page X of Y, prev/next disabled at ends, page reset on filter/clear/page-size change; state in kycGapReport Redux slice with selectors for filter → sort → paginate → modal record — MM-GR07. | In Progress | None | 2026-05-25
|  |  | Tabrez | KYC | KYC Gap Reports | KYC Gap Reports UI Development | “Report List” row with five filters: search (customer name / ID), All Branches (name + code in label), All Customer Types, All Templates, All Priorities (Low / Medium / High / Critical only). Second filter row: “Filter by:”, Gap Score Min–Max numeric inputs, and Clear Filters resetting all filters and pagination to page 1. Nine-column read-only table with correct columns, sort toggles on required columns, Individual/Corporate and priority badges, monospace Customer ID / Branch Code, KYC Gap Score + risk pill, purple eye action, hover styling, and all 12 Figma sample customers in gap-report.seed.ts; no Missing Fields, Gap Type, Edit, or Bulk Notify columns. | Completed | None | 2026-05-22
|  | Backend | Arun | KYC | Customer 360 | Customer 360 Data Model & API Development | Generated pseudocode and finalized low-level design for Customer 360 implementation. Designed a unified API to support all Customer 360 UI screens and tabs. Created backend models, repositories, services, and controller structure. Mapped UI requirements to API response models and database entities. Working on Customer 360 API integration and backend implementation | Completed | None
|  |  | Santosh | KYC | Missing Mandatory | Missing Mandatory Data Model & API Development | Generated pseudocode and finalized low-level design for the Missing Mandatory module. Analyzed UI requirements and designed APIs to support report generation and dashboard views. Created backend models, repositories, services, and controller structure for the module. Mapped business rules, validation logic, and database tables to report APIs and response models. | Completed | None
|  | QA | Arti Kunde | KYC | KYC/Missing Mandatory / Gap Reports | Missing Mandatory and Gap Reports test case writing | Yesterday: Worked on Missing Mandatory module test case coverage for field configuration, Individual and Corporate template behavior, CDD/EDD sections, Technical IDs, field mapping, and validation-related scenarios. Today: Will continue covering remaining Missing Mandatory module test cases focusing on KYC Gap Report filtering, search behavior, sorting, pagination, report detail validations, state persistence, and report workflow-related scenarios. | Completed | None | 2026-05-22
|  |  | Sanket Kirar | KYC | KYC/Missing Mandatory / Gap Reports | Missing Mandatory and Gap Reports test case writing | Yesterday: Worked on Missing Mandatory module test case coverage for versioning, save flow validations, score calculation logic, score mapping, boundary validations, template synchronization, and initial KYC Gap Report-related scenarios. Today: Will continue covering remaining Missing Mandatory module test cases focusing on score calculation engine, missing field logic, RBAC validations, session handling, security scenarios, final review, and completion of Missing Mandatory module test case coverage. | Completed | None | 2026-05-22
|  | DevOps | DevOps 1 |  | Awaiting for the confirmation on the new server

## W2 – 26 May
📋 Daily Task Update Tracker ¦ Week 2 (26 May – 30 May 2026)
Day | Date | Team | Developer | Module | Sub Module/ Task Title | Dev Phases | Description / Update | Status | Blockers / Notes | ETA / Due
Monday | 2026-05-25 | Frontend | Khizar | KYC | KYC Gap report BFF Layer | Design - Prepare BFF/API requirement documentation, including endpoint definitions | 1- Started implementation of KYC Gap Reports BFF layer structure and initial API integration flow. 2- Working on tab-level API segregation for KYC Gap Reports to support scalable and modular data loading. 3- Designing frontend-to-BFF integration flow aligned with Customer 360 architecture patterns. 4- Analyzing KYC Gap Reports response structure, pagination strategy, and performance optimization for large report datasets. | Completed |  | 25/05/2026
|  |  | Aditya | Screening | Manual Screening UI | Manual Screening UI Development | Top bar: title, View Last Results Tabs: Manual Screening and Bulk Upload Entity toggle: Individual, Non-Individuals, Vessel All form fields, watchlist cards, and license warning. | Completed |  | 25/05/2026
|  |  | Tabrez | Screening | Manual Screening UI | Manual Screening UI Development | Host submenu: Sanctions Screening → Manual Screening (/screening/manual-screening) Regenerated MF manifest / sidebar nav from mf.config.json Bulk upload & screening results UI :- Results: subject card, GenAI summary, 5 KPI stats Results table: 6 demo rows, filters, score bars, badges | Completed |  | 25/05/2026
|  | Backend | Arun | KYC | Customer 360 | Customer 360 Data Model & API Development | Incremental status update for Customer 360: Integrated Customer 360 APIs with the UI and performed end-to-end testing. Collaborated with the UI team to validate data mapping and API response structures. Refactored the initial single-API design into multiple APIs to improve performance and reduce response time. Enhanced and optimized pseudocode, low-level design, and backend architecture based on integration feedback. Refactored service, controller, and data aggregation logic to support scalable and efficient UI integration. | Completed
|  |  | Santosh | KYC | Customer 360 |  | Analyzed the field values to be computed and shown in databse tables; identified the fileds, how to compute the values, source tables of the dependent fields, target table columns where computed values to be stored | Completed |  | 25/5/2026
|  | QA | Arti Kunde | KYC | Missing Mandatory / Gap Reports | Missing Mandatory / Gap Reports test case writing | covered remaining Missing Mandatory module test cases focusing on KYC Gap Report filtering, search behavior, sorting, pagination, report detail validations, state persistence, report workflow-related scenarios, and Add Field functionality including custom field addition, mandatory/optional field behavior, field configuration, and related edge case validations. | Completed |  | 2026-05-26
|  |  | Sanket Kirar | KYC | Missing Mandatory / Gap Reports | Missing Mandatory / Gap Reports test case writing | Covered remaining Missing Mandatory module test cases focusing on score calculation engine, missing field logic, RBAC validations, session handling, security scenarios, Add Field functionality, and final review of module coverage. Also covered DB edge cases including field validation, duplicate handling, data persistence, UI-DB consistency, and mandatory/optional field mapping validations. | Completed |  | 2026-05-26
|  | DevOps | DevOps 1
Tuesday | 2026-05-26 | Frontend | Khizar | Screening | Manual Screening | Design - Prepare BFF/API requirement documentation, including endpoint definitions | Working on Finalizing Manual Screening BFF API listing and shared the complete details with Arun for BFF layer implementation by tommorow . | In Progress | None | 27/05/2026
|  |  | Aditya | Screening | Batch Screening | Batch Screening UI Development | • Match Results — Main screen with a table of customers who have screening hits (name, ID, scores, list, category, date), plus search, date filter, pagination, and disposition actions per row. • Custom date range — Popup to pick a custom from/to date when filtering results on the landing screen. • Row navigation — Clicking a customer name or list count opens the detail flow where full data is available. | Completed | None | 26/05/2026
|  |  | Tabrez | Screening | Batch Screening | Batch Screening UI Development | • Screening Results — Customer profile card, AI summary banner, risk counts (critical/high/medium), and a table of all matches with disposition, move to exception list, and view actions. • Match Review — Investigation screen with back link, reference ID, report / false positive / confirm match actions, and a confirm-match popup with comments. • Review tabs — AI Summary (alert + GenAI narrative and risk signals); Match Details (overall score, status, subject details, and per-hit cards with attribute comparison and escalate); View Summary (customer and match stats cards plus a weighted comparison table). | Completed | None | 26/05/2026
|  | Backend | Arun | CDC | CDC | Design -Design for CDC, compute and the population into database table columns | Analyzed CDC (Change Data Capture) requirements | Completed | None | 28/5/2026
|  |  | Santosh | KYC | KYC Gap report | KYC Gap Report for Backhand Development | Analyzed UI requirements, database tables, and business logic for the KYC Gap report module. Identified required data sources, validation rules, and report generation logic. | In Progress |  | 2026-02-06
|  | QA | Arti Kunde | KYC/Screening | KYC Gap Score Configuration tab /Batch Screening | KYC Gap Score Configuration Tab / Batch Screening – Screen Analysis & Test Case Writing | Modified and maintained detailed test cases for the KYC Gap Score Configuration tab by validating how computed gap scores are assigned to different risk labels across templates. Covered detailed validation scenarios for how computed KYC gap scores are configured and mapped to different risk labels across templates, including score range validations, configuration behavior, UI validations, workflow checks, and edge case coverage. For Today will take Batch Screening | Completed |  | 2026-05-27
|  |  | Sanket Kirar | KYC | KYC Gap Score Configuration tab /Batch Screening | KYC Gap Score Configuration Tab / Batch Screening – Screen Analysis & Test Case Writing | Modified KYC Gap Score Configuration feature to understand the business logic behind score computation and risk label mapping for different templates. Worked on preparing edge case, negative, and workflow-based scenarios covering boundary values, invalid configurations, dependency validations, and expected system behavior for score-to-risk mapping functionality. Today will start batch screening | Completed |  | 2026-05-27
|  | DevOps | DevOps 1 |  | Testing with the existing pipeline with cc build |  | identifying any gap in current code design and pipeline to make it more modular to make compatible with future docker
Wednesday | 2026-05-27 | Frontend | Khizar | Screening | Batch Screening BFF | Design - Prepare BFF/API requirement documentation, including endpoint definitions | Working on Finalizing Batch Screening BFF API listing and shared the complete details with Arun for BFF layer implementation by tommorow . | In Progress | None | 29/05/2026
|  |  | Aditya | Configuration | Custom List Manager | Custom List Manager UI Development | Lists home screen — Page title, short description, and four summary boxes (total lists, active lists, total entities, pending approval). Lists table — Shows all custom lists with name, status, record counts, action on hit, TTL, dates, and expiry; click list name to open details. Search & filters — Search by list name/status; filter by status; change rows per page; sort columns (name, status, dates, etc.). Create new list — Form panel to enter list name, purpose, default action, TTL, reason, and turn fuzzy matching / multilingual on or off; Save draft and Submit for approval buttons. | In Progress | None | 29/05/2026
|  |  | Tabrez | Configuration | Custom List Manager | Custom List Manager UI Development | Bulk upload panel — File upload UI, template download, validation summary modal (seed data). List detail — Metadata section + entity table with search, filters, sort, and pagination. State & i18n — Redux customListManager slice, fixture seeds, custom-list-manager.css, and English labels in screening.json. | Completed | None | 29/05/2026
|  | Backend | Arun | CDC | Design for CDC, compute and the population into database table columns | Design for CDC, compute and the population into database table columns | Analyzed CDC (Change Data Capture) processing concepts for capturing source system data changes and propagating them to target databases. Evaluated various CDC tools including Debezium, Oracle GoldenGate, Maxwell, and SQL Server CDC for Customer 360 use cases. Conducted technical exploration of Debezium for real-time change data capture and event-driven data synchronization. Designed an approach to integrate CDC-based data ingestion with the Customer 360 data model and APIs. | Completed |  | 28/5/2026
|  |  | Santosh | UAC | CC local installation and integration with CC UAC | Integration |  | In Progress |  | 29/5/2026
|  |  | Dev 3 | KYC | Missing document template, kyc gap report | Design -Missing document template, kyc gap report |  | In Progress |  | 2026-02-06
|  | QA | Arti Kunde | Sanctions Screening | Batch Screening | Batch Screening – Screen Analysis & Test Case Writing | Covered test case writing for Batch Upload Flow, Forward/Reverse Screening, Bulk Processing, File Validation, Mandatory Columns, Template Mismatch, Row Parsing, Duplicate Rows, Partial Success/Partial Fail, and Invalid Row Segregation scenarios. Also covered Queue/Running/Completed/Failed status handling, Retry/Re-upload flow, Batch Summary Integrity, Row-level Results, Score/Severity Mapping, Export Integrity, and regression/negative/boundary validations. | Completed |  | 2026-05-28
|  |  | Sanket Kirar | Sanctions Screening | Batch Screening | Batch Screening – Screen Analysis & Test Case Writing | Covered Batch Screening Foundation, Entry Flow, Navigation, Batch Landing page, Access Control, and Initial Load validations as part of test case writing activities. Worked on Upload Zone, File Selection, Drag & Drop functionality, File Intake validations, Refresh/Session Persistence, Watchlist Profile Consistency, Stale Batch Prevention, and RBAC/Audit-related behavior coverage. | Completed |  | 2026-05-28
|  | DevOps | DevOps 1 |  | check for any issue with the cc
Thursday | 2026-05-28 | Frontend | Khizar |  | On Leave |  | On Leave
|  |  | Aditya | Configuration | Custom List Manager | Custom List Manager UI Development | New Audit trail page under Custom List Manager in the side menu. Shows page title and short note about secure, long-term audit logging. Search box to find events by text or event ID. Filters: event type, user, and date range (from / to). Export CSV / PDF buttons on screen (not connected to backend yet). Event list as a timeline: colored dot, title, details (who did what, request ID), date/time. Pagination at the bottom (e.g. “Showing 1–7 of 9,182 events”). Uses sample data in the UI for now (no live API). | In Progress |  | 29/05/2026
|  |  | Tabrez |  | On Leave |  | On Leave |  |  | 29/05/2026
|  | Backend | Arun | KYC/CDC | Customer 360 | Design for CDC, compute and the population into database table columns | Applied CDC concepts to the Customer 360 framework for testing and validation of near real-time data updates. Analyzed source-to-target data mapping and change propagation mechanisms for Customer 360 entities. Evaluated Debezium-based architecture for maintaining Customer 360 data consistency across multiple source systems. Refined API design and data processing flow to support CDC-driven updates in Customer 360. | In Progress |  | 28/5/2026
|  |  | Arun | CDC | Propagte CDC to UI in near real time |  |  | In Progress |  | 29/5/2026
|  |  | Sushma | CDC | UAC | CC local installation and integration with CC UAC |  | In Progress |  | 29/5/2026
|  |  | Santosh | KYC | Missing Mandatory/KYC gap report |  | Design for Missing document template, kyc gap report | In Progress |  | 2026-02-06
|  | QA | Arti Kunde | Sanctions Screening | Batch Screening / Manual Screening | Batch Screening / Manual Screening– Screen Analysis & Test Case Writing | Reviewed the updated Batch Screening document and modified existing test cases accordingly. Covered scenarios related to batch upload processing, file validations, data parsing, duplicate handling, partial success/failure processing, status transitions, retry functionality, result mapping, export validations, and workflow-related scenarios. Also cross-verified Manual Screening test cases against the latest FSD, frontend implementation, and Figma designs, and updated test cases wherever gaps or requirement changes were identified. | Completed |  | 2026-05-28
|  |  | Sanket Kirar | Sanctions Screening | Batch Screening / Manual Screening | Batch Screening / Manual Screening– Screen Analysis & Test Case Writing | Continued Batch Screening test case updates based on the latest requirement document, covering module flow, upload journey, access validations, file intake behavior, session persistence, audit-related validations, and end-to-end batch processing workflows. Reviewed and refined Manual Screening test cases prepared by other QA members by validating them against user stories, acceptance criteria, Figma designs, frontend implementation, and FSD to ensure complete and accurate test coverage. | Completed |  | 2026-05-28
|  | DevOps | DevOps 1
Friday | 2026-05-29 | Frontend | Khizar | Sanctions Screening | Batch/ManualScreening | Design - Prepare BFF/API requirement documentation, including endpoint definitions
|  |  | Adittiya |  | Custom List Manager | Custom List Manager UI Development
|  |  | Tabrez |  | On Leave
|  | Backend | Arun | KYC/CDC | Customer 360 | Design for CDC, compute and the population into database table columns | Prepared an analysis sheet to identify suitable CDC use cases. Identified high-volume and heavy-computation entities for selective CDC implementation. Documented CDC feasibility and implementation strategy for Customer 360. | Completed
|  |  | Santosh | KYC | KYC Gap Report | KYC Gap Report for backhand Development | Generated pseudocode and finalized low-level design for the Missing Mandatory module. Analyzed UI requirements and designed APIs to support report generation and dashboard views. Created backend models, repositories, services, and controller structure for the module. Mapped business rules, validation logic, and database tables to report APIs and response models. | In Progress
|  | QA | Arti Kunde | Configuration | Custom List Manager | Custom List Manager - Test Case writing | Custom List Manager test case design covering list management, entity management, Maker-Checker workflow, validations, audit trail, and business flow scenarios. Also reviewed test cases created by other QA members and modifying test cases as per figma and fsd | Completed
|  |  | Sanket Kirar | Configuration | custom List Manager | Custom List Manager - Test Case writing | covering Bulk Upload functionality, TTL expiry management, screening-related validations, and associated test scenarios. Also reviewed and updated test cases created by other QA members to ensure alignment with the FSD and business requirements. | Completed
|  | DevOps | DevOps 1

## W3 – 02 Jun
📋 Daily Task Update Tracker ¦ Week 3 (02 Jun – 06 Jun 2026)
Day | Date | Team | Developer | Module | Sub Module/ Task Title | Dev Phases | Description / Update | Status | Blockers / Notes | ETA / Due
Monday | 2026-06-01 | Frontend | Khizar | Sanction Screening | Dedup Screening | Design - Prepare BFF/API requirement documentation, including endpoint definitions | Working on Finalizing Dedup Screening BFF API listing
|  |  | Aditya | Sanction Screening | Dedup Screening | Dedup Screen UI Deveplopment | Set search criteria — Pick one or more match parameters (DOB, Passport, PAN, Mobile, Email, etc.) and optionally enter a Customer ID. Generate Report — System runs de-duplication and shows the De-Duplication Match Report (scrolls to results). Review matches — Table lists duplicate groups (e.g. GRP-0001) with customer IDs, names, matched parameters, and ID numbers. Compare — Compare opens a side-by-side KYC modal (12 fields) with matched fields highlighted. Export — Excel, CSV, PDF, or Print (toast confirmation; real file export when BFF is connected). | Completed | None | 2026-06-01
|  |  | Tabrez | Sanction Screening | on leave
|  | Backend | Arun | Sanctions Screening | Manual Screening | Manual Screening for Backhand Devlopment | Reviewed and analyzed Manual Screening requirements, workflows, and business rules. Performed Manual Screening data model analysis based on FRD and UI requirements. | In Progress
|  |  | Sushma | CC | CC/UAC integration |  | I made the required changes to build all services within the root project structure and resolved the build-related issues. We successfully generated the installer; however, the generated installer structure is not matching the expected CC file structure. I am currently working with Vishnu to identify the gap and make the necessary changes. | In Progress
|  |  | Santosh | KYC | Reference Data Register | Reference Data Register for Backhand Devlopment | Reviewed and analyzed Reference Data Registry requirements, workflows, and business rules. Performed Reference Data Registry data model analysis based on FRD and UI requirements. | In Progress
|  | QA | Arti Kunde | Configuration | Custom List Manager/Exception List Manager | Custom List Manager screen analysis /Exception List Manager - Test case writing | Worked on Custom List Manager test case design by analyzing the FSD in detail, covering Custom List lifecycle, list creation, view/edit functionality, enable/disable workflows, Entity Management, entity data model validations, Maker-Checker approval workflow, request status handling, approval/rejection scenarios, RBAC validations, View History functionality, audit trail tracking, and end-to-end validation scenarios for list and entity management.
|  |  | Sanket Kirar | Configuration | Custom List Manager/Exception List Manager | Custom List Manager screen analysis /Exception List Manager - Test case writing | Completed test case design by analyzing the FSD, covering Bulk Upload functionality, TTL expiry management, screening engine integration, advanced matching capabilities (fuzzy, multilingual, and digital identifier screening), API synchronization, notifications, and related validation scenarios.
|  | DevOps | DevOps 1
Tuesday | 2026-06-02 | Frontend | Khizar | Sanction Screening | Dedup Screening | Design - Prepare BFF/API requirement documentation, including endpoint definitions | It is partially completed. We have a few clarifications pending from the business team. Once we receive the necessary details, we will complete the remaining work and share it with the backend team.
|  |  | Aditya | KYC | Reference Data Register / Customer & Account Data | Reference Data Register UI Deveplopment | RDR — Customer & Account Data Tab(UI) Customer tab :- KPI cards (active / inactive counts) Customer Type dropdown filter + Clear Search bar Columns button (show/hide fields, visible/total count) Data table with scroll (sticky header) View action + detail popup on Customer ID CSV, Excel, Refresh CBS toolbar Max 50K rows export note Account tab :- Filter by Customer ID (CIF) + Clear Search bar Columns button (show/hide fields) Data table with scroll (sticky header) CSV, Excel, Refresh CBS Button Max 50K rows export note.(All tabs completed for Customer & Account Data tab) | Completed | None | 2026-06-02
|  |  | Tabrez |  | on leave
|  | Backend | Arun | Sanctions Screening | Manual Screening | Manual Screening for Backhand Devlopment | 1 .Analyzed the KYC module from a deployment perspective, identifying modules suitable for microservices and those that should remain independent. 2. Attended a KT session with Vishnu on fuzzy logic. 3. Reviewed and analyzed the NFRs for the Manual Screening module.
|  |  | Sushma | UAC | CC/UAC integration |  | Worked with Vishnu to resolve installer generation issues. aAdded the required scripts and migrated the build configuration from Kotlin to Groovy, which enabled the successful execution of fbuild.sh and pack-module.sh. The generated installer now contains the required WAR, JAR, and configuration files.now while uploading the installer in CC getting some Error which we are checking currently the error .
|  |  | Santosh | KYC | KYC/Reference data register
|  | QA | Arti Kunde | Configuration | De-Dup Screening | De Dup Screening test case writing | Worked on De-Dup Screening test case design by analyzing the FSD and UI screens, covering search filter validations, match parameter selection, customer ID filtering, report generation, duplicate group reporting, results table validations, comparison modal validations, export functionality (Excel, CSV, PDF, Print), pagination, and error handling scenarios.
|  |  | Sanket Kirar | Configuration | Ignore Word Configuration/ Keyword Manager | Ignore Word Configuration/ Keyword Manager test case writing | Worked on Keyword Configuration test case design by analyzing the FSD and UI screens, covering page framework, keyword category management, search and filter functionality, table behavior, sorting, row actions, keyword creation and maintenance workflows, bulk upload validations, Maker-Checker approval flow, keyword history tracking, RBAC validations, API and data model validations, business rules, duplicate prevention, security validations, error handling, and end-to-end workflow scenarios.
|  | DevOps | DevOps 1
Wednesday | 2026-06-03 | Frontend | Khizar | Reference Data Register | Reference Data Register | Worked on Assigmnets by Sandeep Seep | Converted the UN SDN[XML] file into CSV and comparee all the filed are algined or not simlarly did for UK fileds
|  |  | Aditya | KYC | Reference Data Register / Cards & Instruments | Reference Data Register UI Deveplopment | RDR — Cards & Instruments (UI only) Section (master) Master tab: Cards & Instruments under Reference Data Register Page title + description (card, mobile, ATM, instrument, device data) Sub-tabs: Card Master, Mobile Banking, ATM Master, Instrument Master, Transaction Device Horizontal sub-tab navigation with active state Shared UI (all 5 tabs) Search bar (filters rows in the current tab) Record count + last-sync line on the table card Read-only data table with vertical/horizontal scroll and sticky header View action per row → detail popup Toolbar: CSV, Excel, Refresh CBS (disabled) Max 50K rows export note No column show/hide picker on these tabs | Completed | None | 2026-06-03
|  |  | Tabrez |  | on leave
|  | Backend | Arun | Sanctions Screening | Manual Screening | Manual Screening for Backhand Devlopment | 1. Analyzed the Name Screening documentation and design documents, including the fuzzy matching algorithms used for screening. 2. Analyzed the integration approach and identified how the Name Screening engine can be integrated into the current system architecture. 3. Started the analysis of the Screening Configuration and Data modules for the FR. Once this analysis is completed, we can proceed with the implementation of the Screening module, as it has dependencies on screening .
|  |  | Sushma | CC Integration | CC/UAC integration |  | I identified multiple issues during the CC deployment process, including missing stop script files, file format errors, API deployment errors, and missing database entries. Further analysis and support from the CC team are required to resolve these issues. We were unable to connect with the CC team yesterday as they were unavaiable and waiting for availability from cc team.
|  |  | Santosh | KYC | KYC/Reference data register
|  |  | Arti Kunde | KYC | Reference Data Register writing testcases /Customer 360, Missing mandatory, KYC gap report testing not start yet | Customer 360, Missing Mandatory & KYC Gap Report – Automation Framework Setup | Working on Reference Data Register (RDR) test case design by analyzing the FSD & UI Screens covering module navigation, search and filter functionality, data grid validations, column selector behavior, detail view screens, export functionality, role-based access validations, and Country Master Maker-Checker workflow scenarios.
|  |  | Sanket Kirar | KYC | Reference Data Register writing testcases /Customer 360, Missing mandatory, KYC gap report testing not start yet | Customer 360, Missing Mandatory & KYC Gap Report – Automation Framework Setup | overing Customer & Accounts, Cards & Instruments, Relationships & Parties, Employee Master, master data validations, data visibility checks, field-level validations, filter combinations, and cross-module data consistency scenarios.
|  | DevOps | DevOps 1
Thursday | 2026-06-04 | Frontend | Khizar | KYC | Reference Data Register | Design - Prepare BFF/API requirement documentation, including endpoint definitions | Worked on Finalizing Manual Screening BFF API listing and shared the complete details with Arun for BFF layer implementation by tommorow .
|  |  | Aditya | KYC | Reference Data Register / Relationships & Related Parties & Reference Masters | Reference Data Register UI Deveplopment | Worked on Relationships & Related Parties & Reference Masters completed the UI also involve in a call for a Reverse KT and watchlist configuration changes | Completed | None | 2026-06-04
|  |  | Tabrez |  | on leave
|  | Backend | Arun | Screening | Manual Screening | Manual Screening for Backhand Devlopment | Started working on a dummy implementation for the Screening module to understand the end-to-end functional flow. Current focus areas: Watchlist Upload Watchlist Rule Configuration Manual Screening OpenSearch & Fuzzy Logic Integration Currently working on the first phase: watchlist upload, data storage, OpenSearch installation, and indexing flow. Subsequent phases will cover rule configuration, screening execution, fuzzy matching, and manual screening workflows.
|  |  | Sushma | CC Integration | CC/UAC integration |  | The issues encountered during deployment were resolved with support from the CC team,yesterday and the deployment was completed successfully. The logs confirm that the service is up and running. The next step is to learn and perform authentication flow testing to validate the deployment.
|  |  | Santosh | KYC | KYC/Reference data register
|  |  | Arti Kunde | KYC | Reference Data Register | Reference Data Register test case writing in progess | Worked on Reference Data Register test case design by analyzing customer and account data modules, covering Customer Master, Customer Address, Customer Documents, Risk Assessment, Account Master, Customer-Account Relationship, Loan Account, and EOD Balance validations. Also covered field-level validations, data integrity checks, business rules, relationship mapping, and end-to-end workflow scenarios.
|  |  | Sanket Kirar | KYC | Reference Data Register | Reference Data Register test case writing in progess | Worked on Reference Data Register test case design covering Cards & Instruments, Mobile Banking, ATM Master, Instruments, Transaction Device, Beneficial Owner, Related Parties Network, and Non-Customer Master modules. Also covered data mapping validations, relationship validations, reference data consistency, negative scenarios, and business workflow coverage.
|  | DevOps | DevOps 1
Friday | 2026-06-05 | Frontend | Khizar | KYC | Reference Data Register | Design - Prepare BFF/API requirement documentation, including endpoint definitions | Worked on API Integration | Completed
|  |  | Aditya | KYC | Reference Data Register / Employee Master | Reference Data Register UI Deveplopment | Completed Employee master. | Completed | None | 2026-06-05
|  |  | Tabrez |  | on leave
|  | Backend | Arun | Screening | Manual Screening | Manual Screening for Backhand Devlopment | 1. Created the initial pseudo code and completed the setup for watchlist ingestion. 2. Loaded and indexed three watchlists (OFAC SDN, OFAC Non-SDN, and UN Consolidated) into the database and OpenSearch. 3. Configured the Rule Engine as per the shared FRD, including watchlist selection, thresholds, and rule configuration flow.
|  |  | Santosh | CDC | CDC Design updates
|  | QA | Arti Kunde | Framework Setup /Sanction Screening | Framework Setup / Sanction MIS Reports | Agentic AI Automation Framework Setup | Completed the initial Playwright MCP framework setup and folder structure. Currently analyzing how Agents, Skills, and Rules can be integrated into the framework.
|  |  | Sanket Kirar | Sanction Screening | Sanction MIS Reports | Sanction MIS Reports screen analysis and test case writing | Worked on Sanction MIS Reports test case design covering Comprehensive Sanctions Screening Intelligence Report, Enhanced Due Diligence (PEP & Adverse Media Analytics), Screening Exception Authorization & Tracking Report, Screening Logic Governance & Change Control Report, Exception List Governance & Accountability Report, configuration validations, RBAC scenarios, audit trail coverage, security validations, and identified gap coverage scenarios to ensure complete report validation and compliance workflow coverage
|  | DevOps | DevOps 1

## W4 – 09 Jun
📋 Daily Task Update Tracker ¦ Week 4 (09 Jun – 13 Jun 2026)
Day | Date | Team | Developer | Module | Sub Module/ Task Title | Dev Phases | Description / Update | Status | Blockers / Notes | ETA / Due
Monday | 2026-06-08 | Frontend | Khizar | Repo | Structure | worked on new repo structure | Seprated Repos from mono repo to Seaprate repo for Micro FE
|  |  | Aditya | Sanctions Screening | Sanction Screening/Screening MIS Reports | Screening MIS Reports UI Development | Completed Sanction MIS Reports UI Development. | Completed |  | 2026-06-08
|  |  | Tabrez | On Leave | On Leave | On Leave
|  | Backend | Arun | Sanctions Screening | Manual Screening | Manual Screening for Backhand Devlopment | 1. Created the initial pseudo code and implementation structure for the Screening Engine. 2. Started development of the Manual Screening module. 3. Integrated the provided TAS fuzzy matching JAR into the screening workflow. 4. Working on screening match evaluation and end-to-end Manual Screening flow integration. 5. Analyzing and implementing the screening engine components based on the provided functional requirements.
|  |  | Santosh | DevOps | Work with DevOps to deploy FE/BE code in Dev env.
|  |  | Sushma | UAC | CC/UAC integration |  | Working on preparing the DEV environment for QA testing. Also collaborating with Vishnu on config-management.
|  |  | Arti Kunde | KYC/Configuration | Automation Framework Setup / Customer 360, Custom List Manager and Exception List Manager | Automation Framework Setup / Customer 360, Custom List Manager and Exception List Manager start Automation Test Execution | Completed the initial Playwright MCP framework setup, folder structure, and integration of Agents, Skills, and Rules. Identified a few dependencies that need to be installed to complete the framework setup. | Completed
|  |  | Sanket Kirar | Sanction Screening | Sanction MIS Reports | Sanction MIS Reports – Screen Analysis & Test Case Writing | Continued Sanction MIS Reports test case design by analyzing report configuration workflows, dashboard counters, report generation behavior, search and filter functionality, date range validations, governance reports, exception tracking reports, audit trail coverage, RBAC validations, export functionality, and end-to-end reporting workflow scenarios. Also reviewed business rules and refined test cases to ensure complete compliance reporting coverage. | Completed
|  | DevOps | DevOps 1
Tuesday | 2026-06-09 | Frontend | Khizar | Repo | Structure | worked on new repo structure | Seprated Repos from mono repo to Seaprate repo for Micro FE
|  |  | Aditya | Configuration | Sanction Screening Config | Design Sanction Screening Config | Create / Edit wizard — 5 steps: Basic Info, List Selection, Field Mapping, Match Score, Result Config + summary; save watchlist. | Completed | None | 2026-06-09
|  |  | Tabrez | Configuration | Screening Config | Screening Config | Watchlist landing — Tabs, search, table (name, type, score, date, status), row actions (view, edit, enable/disable). Enable / Disable modal — Action, date, username, reason, submit. View Details panel — Basic info, included lists, match score config, edit button. | Completed | None | 2026-06-09
|  | Backend | Arun | Configuration | Custom lists | Design review and Backhand Devlopment | 1. Analyzed the FRD for the Custom List in the Configuration Module. 2. Prepared initial pseudo code and implementation structure for the Custom List feature. 3. Analyzed the FRD for the Ignore Words Configuration in the Configuration Module.
|  |  | Santosh | CC | Ensure all services are deployed in Dev CC
|  |  | Santosh | Configuration | CC/Configuration integration
|  |  | Arti Kunde | Configuration | Automation framework Setup | Automation Framework Setup | Framework setup completed. Attended the KT session with Lakshmi and the team yesterday, updated the framework structure, and started running basic test cases on demo sites to validate the framework setup. | Completed
|  |  | Sanket Kirar | Configuration | Screening Configuration | Screening Configuration – Test Case Update as per Updated Figma | Updating Screening Configuration test cases based on the latest Figma changes. Reviewing and modifying existing test cases to align with updated UI layouts, workflow changes, field behavior, validation rules, navigation flow, configuration settings, and business requirements. Also performing gap analysis to ensure complete coverage of newly introduced and modified functionality. | Completed
|  | DevOps | DevOps 1
Wednesday | 2026-06-10 | Frontend | Khizar | Configuration | Sanction Screening Config | Design - Prepare BFF/API requirement documentation, including endpoint definitions | Working on Finalizing Sanction Screening Config BFF API listing
|  |  | Aditya | Configuration | Exception List | Exception List UI Development | New exception list form, CSV bulk upload for lists CSV/PDF export. Also moved custom list to config from custom list manager under screening MFE. | Completed | None | 2026-06-10
|  |  | Tabrez | Configuration | Exception List | Exception List UI Deveplopment | Exception Lists landing :- Stats, Active/Suspended/All tabs, search & filters, table, row actions (view, edit, suspend). List Detail page :- List metadata, entries table, filters, row actions (edit, suspend, history). Edit / Suspend modals :- Edit list/entry, suspend/activate, submit for approval. | Completed | None | 2026-06-10
|  | Backend | Arun | Sanction Screening | Batch Screening | Design review and Backhand Devlopment | 1. Analyzed the FRD for the Batch Screening in the Configuration Module. 2. Prepared initial pseudo code and implementation structure for the Custom List feature. 3. Analyzed the FRD for the De-Duplication Screening in the Sanction Screening Module.
|  |  | Santosh | CC | Ensure all services are deployed in Dev CC
|  |  | Santosh | Configuration | CC/Configuration integration
|  |  | Arti Kunde | Screening/Configuration | Manual Screening , Batch Screening , Exception List Manager and Screening Configuration testing start | Manual Screening , Batch Screening , Exception List Manager and Screening Configuration start Automation Test Execution | I validated the Playwright framework by running basic test cases of demo sites and am currently reviewing the framework structure and preparing reusable components for AML module automation
|  |  | Sanket Kirar | Screening/Configuration | Manual Screening , Batch Screening , Exception List Manager and Screening Configuration testing start | Completed local setup review and automation framework analysis for AML testing activities | Reviewed the Playwright framework structure, reusable components, and execution flow. Executed sample test cases to validate framework readiness.
|  | DevOps | DevOps 1
Thursday | 2026-06-11 | Frontend | Khizar | Configuration | Sanction Screening Config | Design - Prepare BFF/API requirement documentation, including endpoint definitions | Working on finalizing it the it will be shared
|  |  | Aditya | Configuration | Keyword manager | Keyword manager UI development | Add Keyword panel — Keyword, category, risk, match type, fuzzy threshold, screening fields, narrative tester & preview; save draft / submit for approval.Add Category modal + Category Controls — New category form; enable/disable categories; Export CSV from toolbar. | Completed | None | 2026-06-11
|  |  | Tabrez | Configuration | Keyword manager | Keyword manager UI development | Keywords landing — Active/Inactive/Drafted tabs, search, table (keyword, category, risk, match type, date, status), row actions (enable, disable, submit). Keyword History panel — Opens on keyword click; keyword details, screening fields, threshold, activity timeline. approval modal — Shown after add, disable, enable, or draft submit. | Completed | None | 2026-06-11
|  | Backend | Arun | Configuration | Exception lists | Design review and Backhand Devlopment | 1. Analyzed the FRD for the Exception listsin the Configuration Module. 2. Prepared initial pseudo code and implementation structure for the Exception List feature .
|  |  | Santosh | Configuration | CC/Configuration integration
|  |  | Arti Kunde | Screening/Configuration | Manual Screening , Batch Screening , Exception List Manager and Screening Configuration testing start | Manual Screening , Batch Screening , Exception List Manager and Screening Configuration start Automation Test Execution | Completed the local setup, exploring the application flow, and start testing in the local environment | Completed
|  |  | Sanket Kirar | Screening/Configuration | Manual Screening , Batch Screening , Exception List Manager and Screening Configuration testing start | Started testing Reference Data Registry in the local environment. Reviewed screens and module workflows. | Completed local setup activities and synchronized the latest project codebase. Verified application accessibility, validated environment configuration, reviewed application structure, and prepared the local environment for functional testing and automation activities | Completed
|  | DevOps | DevOps 1
Friday | 2026-06-12 | Frontend | Khizar | Sanctions Screening | Screening configuration | Design - Prepare BFF/API requirement documentation, including endpoint definitions | Design - Prepare BFF/API requirement documentation, including endpoint definitions done and shared with Backend team
|  |  | Aditya | Configuration | Ignore words | Ignore words UI development | Add Keyword panel — Keyword, category, risk, match type, fuzzy threshold, screening fields, narrative tester & preview; save draft / submit for approval. Add Category modal + Category Controls — New category form; enable/disable categories; Export CSV from toolbar. |  |  | 2026-06-12
|  |  | Tabrez | Configuration | Ignore words | Ignore words UI development | Ignore Words landing — Active/Inactive/Drafted tabs, search, table (word, category, risk, match type, date, status), row actions (enable, disable, submit). Word History panel — Opens on word click; word details, category/risk/match badges, activity timeline. Approval modal — Shown after add, disable, enable, or draft submit.
|  | Backend | Arun | Configuration | Keyword Manager and Ignore Words Configuration | Design review and Backhand Devlopment | 1. Analyzed the FRD for the Ignore Words Configuration in the Configuration Module. 2. Prepared initial pseudo code and implementation structure for Ignore Words Configuration.
|  |  | Santosh | Configuration | CC/Configuration integration
|  | QA | Rishu Ranjan | Screening/Configuration | Screening Configuration, Batch Screening | Completed the Local setup for testing purpose. Tested Screening Configuration. Batch Screening in progress.
|  |  | Arti Kunde | Screening/Configuration | Manual Screening , Batch Screening , Screening Configuration, Keyword Manager testing start | Completed the Local setup for testing purpose. Tested Missing Mandotory & Kyc Gap Report . Customer 360 in progress. | Performed testing on the Missing Mandatory and KYC Gap Report modules and identified defects. Currently working on Customer 360 testing and reviewing its functionalities. | Completed
|  |  | Sanket Kirar | Screening/Configuration | Manual Screening , Batch Screening , Screening Configuration, Keyword Manager testing start | Continued testing Reference Data Registry. Validated functionality and identified observations during testing. | Started manual testing of the Reference Data Registry module in the local environment. Reviewed screen navigation, master data management workflows, search functionality, grid behavior, data visibility, and overall module functionality to understand business flow and application behavior.
|  | DevOps | DevOps 1

## W5 – 16 Jun
📋 Daily Task Update Tracker ¦ Week 5 (16 Jun – 20 Jun 2026)
Day | Date | Team | Developer | Module | Sub Module/ Task Title | Dev Phases | Description / Update | Status | Blockers / Notes | ETA / Due
Monday | 2026-06-15 | Frontend | Khizar | Deployment | CC Deployment | Alinging CC installer module | Working on CC Alignment module for QA Deploymemt
|  |  | Aditya | Screening | Mismatch in FSD and figma | Mismatch in FSD and figma | NA | Blocked | Blocker due to a technical issue in my laptop
|  |  | Tabrez | Screening | Resolved screening config FE bugs | Resolved screening config FE bugs | Resolved around 18-20 bugs from screening config FE
|  | Backend | Arun | Configuration | Keyword Manager | Design review and Backhand Devlopment | 1. Analyzed the Functional Requirements Document (FRD) for the Keyword Manager within the Configuration Module. 2. Prepared the initial pseudocode and implementation design for the Keyword Manager feature. 3. Initiated testing and validation of the functional requirements to ensure alignment with the specified business and technical requirements.
|  |  | Santosh |  | services structure change to align with CC |  | Make all BE services compatible to deploy in Dev CC
|  | QA | Rishu Ranjan | Screening/Configuration | Screening Configuration, Batch Screening | Tested Screening Configuration on Local Setup. Started automating the test cases in the local setup for localhost URL
|  |  | Arti Kunde | Screening/Configuration | Manual Screening , Batch Screening , Keyword Manager , Ignore Word Configuration testing start | Testing Customer 360 on Local Setup. Started automating the test cases in the local setup for localhost URL | Automation Testing (Local Environment) Wrote and executed Playwright test scripts for the Customer 360 module in the local environment.
|  |  | Sanket Kirar | Screening/Configuration | Manual Screening , Batch Screening , Keyword Manager , Ignore Word Configuration testing start | Completed major Reference Data Registry testing and started Custom List Manager testing. | Started manual testing of the Custom List Manager module. Reviewed list management workflows, configurations, validations, and screen behavior in the local environment.
|  | DevOps | DevOps 1
Tuesday | 2026-06-16 | Frontend | Khizar | Deployment | CC Deployment | Alinging CC installer module
|  |  | Aditya | Screening | Sanction MIS Reports | Sanction MIS Reports UI Deveplopment | Doing RDP access setup and system get slow due to RDP access also ask Raghul to whitelist some of the URLs | Blocked | Yes
|  |  | Tabrez | Screening | Screening config FE bugs | Screening config FE bugs | Fixed around 20 remaining bugs from screening config FE | Completed | No | 2026-06-17
|  | Backend | Arun | Deployment | CC Deployment | Alinging CC installer module | Initiated deployment activities in the CC environment for the following modules: 1. sanctions-screening 2. fuzzy-analysis-service 3. sanctions-screening-configuration Started validation and issue-fixing activities as part of the deployment process.
|  |  | Santosh | Configuration | Generic configuration service | Implementation | Changing the implementation to use AML datatabse in the backend
|  | QA | Rishu Ranjan | KYC | KYC Gap Report, Missing Mandatory | KYC Gap Report, Missing Mandatory automation script completed using the local setup.
|  |  | Arti Kunde | Screening/Configuration | KYC / Customer 360 | KYC / Customer 360 start Automation Test Execution for localhost URL | KYC / Customer 360: Started writing and executing automation test scripts on the localhost environment.
|  |  | Sanket Kirar | Screening/Configuration | Manual Screening , Batch Screening , Keyword Manager , Ignore Word Configuration testing start | Continued Custom List Manager testing and business flow validation in local environment. | Continued validating Custom List Manager workflows, field validations, status management, business rules, and end-to-end functionality.
|  | DevOps | DevOps 1
Wednesday | 2026-06-17 | Frontend | Khizar | Deployment | CC Deployment | Work on merge conflicts and build issues for latest code
|  |  | Adittiya | Config | Sanction screening config UI modified | Sanction screening config UI modified | Modified sanction screening config UI according to the final figma and then also fixed 8-9 bugs from keyword manager from buglist shared by QA team. | Completed | None | 2026-06-17
|  |  | Tabrez | Sanctions Screening | Batch Screening | Batch Screening UI bugs | Batch screening UI bugs fixes from the bug sheet shared by QA team. In the manual screening match review page added, improved UI of custom list and exception list to match to make styling consistent. | Completed | None | 2026-06-17
|  | Backend | Arun | Deployment | CC Deployment | Alinging CC installer module | Successfully deployed the following modules in the CC environment: 1. sanctions-screening 2. fuzzy-analysis-service Resolved deployment and build-related issues encountered during the process and completed the required validation activities successfully.
|  |  | Santosh |  | QA Support
|  | QA | Rishu Ranjan | Screening/Configuration | Dedupe Screening , Ignore Word Configuration, Sanction MIS Reports testing start | Dedupe Screening , Ignore Word Configuration, Sanction MIS Reports start Automation Test Execution
|  |  | Arti Kunde | Screening/Configuration | Dedupe Screening , Ignore Word Configuration, Sanction MIS Reports testing start | KYC / Customer 360 and ignore word configuration start Automation Test Execution for localhost URL | Started automation test execution for Customer 360 and ignore word configuration on the localhost environment.
|  |  | Sanket Kirar | Screening/Configuration | Dedupe Screening , Ignore Word Configuration, Sanction MIS Reports testing start | Completed major Custom List Manager testing and started Reference Data Registry automation development for localhost | Started automation development for RDR by analyzing workflows, identifying locators, preparing reusable components, and creating automation scripts.
|  | DevOps | DevOps 1
Thursday | 2026-06-18 | Frontend | Khizar
Adittiya
|  |  | Tabrez | Config | Custom list UI bug fixes | Custom list UI bug fixes
|  | Backend | Arun | Deployment | CC Deployment | Alinging CC installer module | Successfully deployed sanctions-screening-configuration in the CC environment and resolved the build issues identified during the deployment process. Validation activities have been completed successfully.
|  |  | Santosh |  | QA Support
|  | QA | Rishu Ranjan | Screening/Configuration | Dedupe Screening , Ignore Word Configuration, Sanction MIS Reports testing start | Dedupe Screening , Ignore Word Configuration, Sanction MIS Reports start Automation Test Execution
|  |  | Arti Kunde | Screening/Configuration | Dedupe Screening , Ignore Word Configuration, Sanction MIS Reports testing start | Automation test execution for the Ignore Word Configuration module on localhost | Started automation test execution for the Ignore Word Configuration module on localhost and performed manual testing in the local setup to validate functionality and workflows.
|  |  | Sanket Kirar | Screening/Configuration | Dedupe Screening , Ignore Word Configuration, Sanction MIS Reports testing start | Continued Reference Data Registry automation development and execution in localhost | Executed automation scenarios for the Reference Data Registry module in the local environment. Reviewed execution outcomes, validated automated workflows, refined scripts, and verified module behavior against expected functionality.
|  | DevOps | DevOps 1
Friday | 2026-06-19 | Frontend | Khizar
Adittiya
|  |  | Tabrez | Configuration | Exception List Manager | Exception List Manager UI bug fixes | Fixed around 22-25 bugs of exception list manager from the bugsheet shared by QA team. | Completed | None | 2026-06-19
|  | Backend | Arun | Deployment | CC Deployment | Alinging CC installer module | Initiated deployment activities in the CC environment for the following module: 1. BFF (Backend for Frontend) Service.
|  |  | Santosh |  | QA support
|  | QA | Rishu Ranjan | Sanctions Screening | Dedupe Screening, Sanction MIS Reports testing start | Dedupe Screening, Sanction MIS Reports start Automation Test Execution
|  |  | Arti Kunde | Sanctions Screening | Dedupe Screening, Sanction MIS Reports testing start | Automation test execution for the Exception List Manager and Keyword Manager modules on localhost | Started automation test execution for the Exception List Manager and Keyword Manager modules on localhost. Performed manual testing in the local setup to validate functionality and workflows, and logged identified defects in the bug tracking Excel sheet.
|  |  | Sanket Kirar | Sanctions Screening | Dedupe Screening, Sanction MIS Reports testing start | Completed major Reference Data Registry automation activities and started Custom List Manager automation development for localhost | Started automation implementation for the Custom List Manager module. Developed automation scenarios, configured reusable components, prepared test scripts, and validated automation flow for localhost execution.
|  | DevOps | DevOps 1